**Procurements in excess of €10m during year ended 2022**

|  |  |
| --- | --- |
| **Project Details** | |
| Year: | 2021 |
| Parent Department: | Mayo County Council |
| Name of Contracting Body: | Mayo County Council |
| Name of Project/Description: | N5 Westport to Turlough Road Project |
| **Procurement Details** | |
| Advertisement Date: | 25th May 2018 |
| Tender Advertised in: | Official Journal of the EU (2018/S 099-225295) |
| Awarded to: | Wills BAM Joint Venture |
| EU Contract Award Notice Date: | 28th November 2019 |
| Contract Price: | €128,117,689, excluding VAT |
| **Progress** | |
| Start Date: | Q4 2019 |
| Expected Date of Completion per Contract: | Q4 2022 |
| Spend in Year under Review: | €49,023,573 excluding VAT (including ex Gratia payments) |
| Cumulative Spend to End of Year: | €115,853,902 excluding VAT (including ex Gratia payments) |
| Projected Final Cost: | €156,000,000 excluding VAT and including ex Gratia payments |
| Value of Contract Variations: | Unknown |
| Date of Completion: | Q2 2023 |
| **Outputs** | |
| Expected Output on Completion  (E.G. XX kms of Road, No of units etc) | 20km of Type 2 Dual Carriageway and 7.5km of Single Carriageway |
| Output Achieved to date  (E.G. X kms of Roads, No of Units etc) | By end of 2022 site clearance, earthworks, drainage, utilities, structures and pavement are 90% complete.  Accommodation works, landscaping, barriers and signage and lighting are 50% complete. |

**Procurements in excess of €10m during year ended 2022**

|  |  |
| --- | --- |
| **Project Details** | |
| Year: | 2022 |
| Parent Department: | Mayo County Council |
| Name of Contracting Body: | Mayo County Council |
| Name of Project/Description: | N60 Balla to Claremorris Road Realignment at Heathlawn |
| **Procurement Details** | |
| Advertisement Date: | 6th May 2022 |
| Tender Advertised in: | Official Journal of the EU (2022/S 089-238861) |
| Awarded to: | P & D Lydon Ltd |
| EU Contract Award Notice Date: | 11th November 2022 |
| Contract Price: | €11,533,339.90 excluding VAT |
| **Progress** | |
| Start Date: | Q4 2022 |
| Expected Date of Completion per Contract: | 10th July 2024 |
| Spend in Year under Review: | €554,077.33 excluding VAT |
| Cumulative Spend to End of Year: | €554,077.33 excluding VAT |
| Projected Final Cost: | €11,533,339.60, excluding VAT |
| Value of Contract Variations: | Unknown |
| Date of Completion: | Q3 2024 |
| **Outputs** | |
| Expected Output on Completion  (E.G. XX kms of Road, No of units etc) | 3.6km of Type 2 Single Carriageway with segregated pedestrian/cycleway. |
| Output Achieved to date  (E.G. X kms of Roads, No of Units etc) | By end of 2022 Contractor has completed set up of site offices and started works for Site Clearance, Fencing and Ducting works along with some utility diversions. |

**Procurements in excess of €10m during year ended 2022**

|  |  |
| --- | --- |
| **Project Details** | |
| Year: | 2022 |
| Parent Department: | Mayo County Council |
| Name of Contracting Body: | Mayo County Council |
| Name of Project/Description: | 50 Unit Housing Development at Golf Course Road, Westport, Co Mayo - A578 |
| **Procurement Details** | |
| Advertisement Date: | 08-04-2022 |
| Tender Advertised in: | e-Tenders |
| Awarded to: | LPB Building Services Ltd. |
| EU Contract Award Notice Date: | 25th November 2022 |
| Contract Price: | €11,143,981.00 |
| **Progress** | |
| Start Date: | 5.12.2022 |
| Expected Date of Completion per Contract: | 4.12.2024 |
| Spend in Year under Review: | N/A – No payments issued in 2022 |
| Cumulative Spend to End of Year: | No payments issued in 2022 |
| Projected Final Cost: | €11,143,981.00 |
| Value of Contract Variations: | N/A |
| Date of Completion: | On-going |
| **Outputs** | |
| Expected Output on Completion  (E.G. XX kms of Road, No of units etc) | 50 Dwelling Units |
| Output Achieved to date  (E.G. X kms of Roads, No of Units etc) | N/A – in construction |